## Sheet1
Area | Metric | Target | Actual | Status (R/Y/G) | Owner | Next Check Date | Notes / Actions
Leasing Pipeline | Qualified tours / week | ≥ 3 |  |  | Leasing |  | If 1–2 = Y: add broker blast + video walkthrough; If 0 = R: reduce ask or increase TI.
Leasing Pipeline | Inbound inquiries / week | ≥ 10 |  |  | Marketing |  | If 5–9 = Y: boost local ads; If <5 = R: refresh photos, price test, add pop-up event.
Leasing Pipeline | LOIs by week 4 | ≥ 1 |  |  | Leasing |  | If 0 by week 4 = R: revisit concept/price/TI.
Budget | Variance vs. plan | ≤ +5% |  |  | PM |  | If +6–10% = Y: VE scope; If >10% = R: scope change or pause for repricing.
Schedule | Inspection pass on first try | Yes |  |  | GC |  | If No = Y/R depending on delay: add pre-walk with inspector.
Schedule | Critical path on time (this week) | On time |  |  | PM |  | If 1–3 days behind = Y; >3 days = R. Add recovery plan.
Risk | Open permit issues | 0 |  |  | Permitting |  | If 1–2 minor = Y; any stop-work or major = R.
Marketing | Listing kit completeness | 100% |  |  | Marketing |  | If missing floorplan/video = Y; missing photos + copy = R.